Project-Management with
OpenOffice.org 2.0 Calc
[Projekt-Management und Gantt-Diagramm mit OpenOffice.org 2.0 Calc and
Comment créer un diagramme de Gantt avec OpenOffice.org]
[Version 2.1.1]
# Content

# Copyright and trademark information
The contents of this documentation are subject to the Public Documentation License, Version 1.0 (the "License"); you may only use this documentation if you comply with the terms of this License. A copy of the License is available at:
http://www.openoffice.org/licenses/PDL.rtf
The Original Documentation is "Comment créer un diagramme de Gantt avec OpenOffice.org". The Initial Writer of the Original Documentation is Serge LE LOUARNE Copyright ©2003. All Rights Reserved.
(Initial Writer contact(s): serge.le_louarne@tiscali.fr.

Contributor(s): DIETMAR HILLER
Portions created by DIETMAR HILLER are Copyright © 2005, 2006. All Rights Reserved.
(Contributor contact(s): webmail.hillerd@cablemail.de.

Contributor(s): G. Roderick Singleton.
Portions created by G. Roderick Singleton are Copyright ©2005. All Rights Reserved.
(Contributor contact(s):grsingleton@openoffice.org .
Portions created by ______ are Copyright ©_________[insert year(s)]. All Rights Reserved. (Contributor contact(s):________________[insert hyperlink/alias]).
All trademarks within this guide belong to legitimate owners.
[Note: a copy of the PDL is included in this template and is also available at: http://www.openoffice.org/licenses/PDL.rtf.]

The associated OpenOffice.org Calc template "PjM_Calc" and the therein contained modules and macros are subject to the GNU Lesser General Public License (LGPL). A copy of the LGPL is available at http://www.gnu.org/licenses/lgpl.html.
## Modifications and updates
Version	Date	Description of Change
[0.9]	[2005-06-06]	dhi: first version (in German)
[1.0]	[2005-11-09]	grs: Initial edition issued for comment
[1.1]	[2005-11-12]	ss: Proofed edition issued for publication
[2.0]	[2006-05-22]	dhi: / - added levels / - unique ID alphanumeric instead of numeric / - separation of predecessors changed from space to ";" / - Columns can be rearranged freely
[2.1]	[2006-05-28]	dhi: - added resource usage analysis - some improvements
[2.1.1]	[]	dhi: / bugfix resource with task duration zero / moved the progress bar to the status line

# Overview
The tasks of a project can be quite complex and dependent on each other. A project management tool allows to divide a project into small sub-units, to visualize the dependencies so that parallel processes can be individuated, the overall processing time determined and progress tracked.
Gantt Charts are a way to graphically show the progress of a project.
This document describes the use of the Calc template "PjM_Calc" to perform simple project management tasks. The Calc sheet contains macros that perform the automatic scheduling of tasks and the evaluation of resource usage.
In this document a relocation-process to another city is used as an examples and is based upon the accompanying Calc template, "PjM_Calc.ots", which is distributed together with this documentation.

Relocation DD to M Illustration 1: The finished example
In illustration 1, the subtasks of the relocation-process appear on the y-axis, and the time line on the x-axis. The bars show when a task should start and when it will be finished.
For those not familiar with project management terms, see
http://www.apm.org.uk/page.asp?categoryID=4&subCategoryID=29&pageID=0 for definitions.
# The Template
The template consists of three sheets:
- "Tasks" – contains the project tasks
- "Gantt" – contains the Gantt chart
- "Resources" – contains information on the resources used
Further custom sheets can be added, but do not rename or delete these three sheets.

The template contains an example project to facilitate the usage
It also includes the macros "Autoschedule" and "Resource Usage" that are explained in detail later-on.
This template uses macros and upon opening displays a security warning. Accept the usage of macros for full functionality.

## The sheet "Tasks"
Abbildung 2: Sheet Tasks
This sheet contains the details of the projects and the activities.
It has a predefined data range "TaskList" that is used by the tool. Do not remove this range. When you add activities make sure the are included in this range. This is best done by adding activities always below the first and above the last activity.
#### Columns
“Info” - Information on the progress of the task
	The task has begun and is on track according to the progress
	The task is completed
	The task is due and not on schedule, this means, that the end-date is prior to the current date.
blank	Task is not due yet, it is not marked.

- “ID” - identifier of the task
- "Level" – tasks can be grouped with this outline level
- “Activity” - description of the task
- “Start” - start-date of the task
- “Duration” - planned or actual duration of the task in calendar days
- “End” - end-date of the task. This gets calculated based on the start-date and duration.
- “Progress” in percentage
- “Done” - Duration * progress
- “Todo” - expected time remaining: Duration - Done
- “Predecessor” - List of tasks, which have to be completed, before this task can start. Separation is made by ";"
Note: The maximum number of predecessors is limited to 9.
"Resource" – Identification of the resource assigned to that task
"Effort" – Effort to perform the task in days or percent of the duration
"Remarks", ... - Further custom column, that are not interpreted by the tool.
The column titles (here located in the third row) can be labeled freely. The positions of the columns can be changed at your choice.
The meaning of the dates is different to what you might be used to from commercial project management tools. For instance take an activity starting on 7-May and ending on 21-June, so lasting 14 days. This means it starts at 7-May 0:00h and ends at 21-June 0:00h. Other more sophisticated tools are using calendars so the same task starts at 7-May 8:00h and ends at
20-June 17:00h.
#### Rows
You can add rows above the table for headers and below for comments but always keep the two heading rows together with the data.
The first header line (in the template the hidden row 2) is used by the macros to identify the columns. Do not change it. You may keep it hidden. If you copy a column (e.g. to create a baseline) delete the content of this row of that column to avoid unexpected results.
It is recommended to use the last row for the end of the project. Insert new tasks above so that they are displayed automatically in the chart.

## The sheet "Gantt"
This sheet contains the Gantt chart. It must be located as unique diagram in the sheet "Gantt".

Abbildung 3: Gantt-chart example
Summary tasks are indicated with black and gray bars, sub tasks in blue and yellow.
Black and blue stand for the accomplished part of the task, whereas gray and yellow indicate the part, that has still to be done.
The horizontal time axis can be scaled e.g. to have a major scaling in weeks, and the sub scaling in days.

Occasionally the bars are not visible. The root cause is still not understood (it could be a bug in OpenOffice.org or caused by the macro). Double click on the Gantt chart which shows the "Format" menu bar. Turn on the legend and assign a color to the data for "todo" and for "done". You can hide the legend again if you want to.

## The sheet "Resources"

Abbildung 4: Sheet "Resources"
The sheet "Resources" allows to calculate the total effort or usage during specific periods of time.
It has a list of resources (here "A4:A7") and time slots (here "B3:H3"). The macro distributes the corresponding effort in these time slots.. The data range "ResourceUsage" is used by the macro to store the calculated values. The last column always contains the effort of the activities after the date of the previous column independently of the header.
The usage below a date (e.g. 21-May) indicates the value from the previous date until 21-May 0:00h or in other words until but not including 21-May!
You can add rows above the table for headers and below for comments but always keep the heading row together with the data.
The graph is an example, how this data can be visualized.
# The Macros
The modules and macros are written in OpenOffice.org BASIC and are located in the Calc template.
## "AutoSchedule"
The macro “AutoSchedule” performs the following process:
- AutoFill: fills in data if missing
  - Duration or end date are set to be calculated
  - Progress is set to 0
  - Done and ToDo formulas are set
  - Level is set to the value of the row above
  - indents task names for sub-tasks
- Analysis of dependencies and sets start dates of depending tasks to the last dates of the predecessors.
- Where the task is finished (Progress = 100%) determines the duration
- Update of the column info
- Update of data for summary tasks
  - Start date is the first date of all sub-tasks
  - end date is the last date of all sub-tasks
  - Progress is the average value of all sub-tasks
- Update of Gantt-Chart
The autoschedule is performed on the data range "TaskList".
The update of the Gantt-Chart is performed for all visible tasks (see also tips and tricks).
During the execution of the macro, a progress bar is shown. After having performed many changes in the task list, the updating of the Gantt chart as the last process step might take some time.
## "ResourceUsage"
- Loops the resources in the sheet "Resources"
  - searches the tasks with that resource name in the task list
  - calculates the total effort per time slot and summarizes per resource
# Using the tool – Managing a Project
The usage of this tool is shown with the example of a relocation to another town.
## Creating a new project
The first step is to create a list of all activities. They can be grouped with the column "LVL", e.g. house-hunting, and canceling of old apartment and banking's order are part of the group activity "original location":

Illustration 5: List of activities
Next insert the start-date for the non-dependent tasks, as well as duration and expected end-date:

Illustration 6: Insert start- and end-date
House-hunting starts on 01/03 and should be finished by 31/08. For all the other tasks the duration is given.
Now, define the dependencies of the tasks. The relocation (700) for example can not start before the new leasing contract is signed (400) and the relocation is organized (500). The tasks 300-9999 do have dependencies, thus there are no predefined start-dates for these tasks.

Illustration 7: Define dependencies
As 20% of house-hunting are already done, and the current apartment is already canceled, the progress is 20% and 100% respectively.
At this point call the macro by clicking on the button “Autoschedule”. The duration and end-dates are calculated, and the column start is completed.

Illustration 8: Calculated duration

Also the Gantt-Chart is updated to show your activities as function of time:

Illustration 9: The appropriate chart
The organization of the relocation, the registration at the office and the opening of an account can be done simultaneously. On the other hand the bank account cannot be moved immediately, because the current apartment is not yet relocated.
## Project controlling
When you begin working on a task, insert the start date in the column “Start”. Set the progress to a value greater than zero (1% e.g.), so that “AutoSchedule” will no longer change this date.
If a task is completed, insert the real End-date, delete the duration and set the progress to 100%. When calling “AutoSchedule” the next time, the required duration will be calculated.
After each change in the table, invoke the macro ”AutoSchedule” to update the table accordingly.
The “Info” column shows the current status of the project:

Illustration 10: Table during project-controlling
House-hunting has begun and is on schedule according to the progress
The apartment has already been canceled, the task is completed.
Cancelling the bank's order is due and not on schedule, this means, that the end-date is prior to the current date.
All the other tasks are not due yet, they are not marked.

## Resource planning
To get an overview of the usage of your resources for instance to see whether they are over-allocated use the columns "Resource" and "Effort" in the "Tasks" sheet together with the sheet "Resources".
Enter the real working time to be spent for each activity. This can be expressed in days or in a percentage to the duration:

Abbildung 11: Resource Efforts (some columns were hidden)
An activity "project management" was added because I intend to spend 10% of my time on the controlling. House hunting will take 2 weeks but the agency will only work 3 days on it etc.
Next switch to the "Resources" sheet and create the table with the list of resources and the periods of interest.
If you need to add date-columns or resources make sure that they are added below the first entry or above the last one to ensure that the macros include them in the calculations.

Calling the function "resource usage" will fill this table.
Between 21-May-06 until but not including 28-May-06 the agency and myself will work on the project 1.1 days and 1.2 days respectively.

Abbildung 12: Table resource usage
You can create graphics from this table such as the following one:

Abbildung 13: Bar Chart Resource Usage
# Tips and tricks
## Today bar
Add on top of your task list a row to indicate the current date in the Gantt chart. This has already been set in the template. Set "level" to "1", "start" to the minimum of all start dates ("=min(...)"), "end" to the current day ("=today()") and "duration" to the difference between end and start ("=G3-E3"). The color can be set with the value of the "progress" (yellow when 0%, blue when 100%).
## Precise planning
The example shows a schedule on a daily basis. It is also possible to plan on hourly basis, even minutes and seconds. Simply set the cell format of the relevant "start" and "end" cell to "time" (e.g. "dd-mm-yy h:mm:ss") and also that of the "duration" to "time" (e.g. "hh:mm:ss").
## Hiding tasks
To simplify the Gantt chart, you may want to hide some tasks. For instance the sub-tasks that are already completed can be hidden, indicating only the summary task. This will also hide these tasks in the Gantt chart. Make sure you call the "Autoschedule" macro to set the correct colors for the tasks.
"Autoschedule" will still analyze these hidden tasks.
## Effort for project management
As project manager you may want to add a task for your activity to take into account your daily work to follow up.
Create an activity for this, set the effort to let's say "10%", set "Start" to the minimum of all start dates ("=min(...)"), "End" to their maximum ("=max(...)") and duration to the difference.
## Using the chart as a graphic in other applications
To use the Gantt-chart as a picture in another application, save the whole Calc document as HTML. This generates not only the HTML-file, but also a jpeg-file containing the chart which can then be included in other documents, such as an OpenOffice.org impress presentation.
Remember to give the graphic a more descriptive name than the name suggested when the document is exported to HTML so that it can be found easily later

# Appendix: Generation of a Gantt-Chart
## Starting the Process
To chart a project, all the sub-tasks must first be collected in a spreadsheet. In this simple example there is the name of the task, the start-date and the duration in calendar days:

Illustration 14: Task list
This simplified project consists of eight subtasks “Task 1” to “Task 8”.
Next, begin creating the chart by selecting Insert—Chart:

Illustration 15: Create the chart
From the dialogue “AutoFormat Chart” define the selection range. Neither the first row (containing the column label) nor the first column (containing the task name) should be included as data.

Click “Next >>” , and choose the Chart type:

Illustration 16: Choose chart type

Choose the horizontal bar-chart and click “Columns” to indicate that the data are arranged in columnar form.
Note: This changes the assignment of the axis in OpenOffice.org Calc. Now the horizontal axis is called “Y” and the vertical axis is called “X”.
Click “Next >>” and choose the variant “Stacked”:

Illustration 17: Create chart with stacked bars

Click “Next >>” once again and enter chart and axis titles:

Illustration 18: Adapt chart labeling

The first Gantt Chart appears as follows:

Illustration 19: Bar chart

The task names are on the vertical axis (“Task 1” to “Task 8”) and the time line is on the horizontal axis.

## Converting the simple bar-chart into a Gantt chart
In order to edit the properties of an element in the diagram,. double-click the chart to select it. Next, right-click to open the context menu and gain access to the chart properties.

Illustration 20: Edit diagram properties
Note: Ensure that no element in the diagram is selected, because otherwise the axis-properties can not be edited
Select the y-axis, which now is the horizontal time line. (One could also select the horizontal axis using a left-click then right-click to open the context menu and finally choose Object Properties ... to format this axis.)
Set the Minimum to the real start-date, In this example this is 01/01/05. Furthermore the axis should get the start date, so check the checkbox “Automatic” in the line “Axis at”:

Illustration 21: Adjust the time line
This produces a chart as follows:
Illustration 22: Gantt chart

The orange bar symbolizes the time up to the start of the task. This bar should be made invisible. For this select the orange bar with a left-click, and then open its Object Properties after a right click.

Under the tab “Borders” choose Style – Invisible, and under the tab “Area” choose Fill – None. Now the chart presents itself as follows:

Illustration 23: The completed Gantt chart

# Appendix: Software documentation
## Module "License"
The module "License" contains the license conditions for all modules and macros for this template.
## Module "Commons"
This module contains those functions that are common to the various modules in this template

Key variables and constants
Dim Col_No() as integer
- contains the column number of the information in the following indicies
- 0:INFO, 1:ID, 2:LVL, 3:Name, 4:Start, 5:Duration, 6:End, 7:Progress, 8:done, 9:todo,
  10: predecessor, 11:resource, 12:effort

Sub InitDocument()
initializes the document

Sub DoneDocument()
terminates the usage of the document

Sub InitTaskTable(oSheet)
initializes the sheet "Tasks"

Progress Bar
Sub InitProgressBar(header, iNumSteps%)
Loads the progress bar, sets the header and the number of steps
Sub IncreaseProgressBar()
increase value of progressbar bar

Sub DoneProgressBar()
hides the progress bar

## Module "AutoSchedule"
Main Functions
Sub Init()
initialization routines

Sub AutoFill (oWhichSheet, iFirstRow, iLastRow)
fill in missing data in table

Sub AnalyseDependencies(Row%, prec$)
set start date according to dependencies

Sub SetSumTaskDates
iterates through the task list and calls SetSumTaskDatesIt(i&)

Function SetSumTaskDatesIt(i&) as long
- sets the dates (start, duration, end) for summary tasks – iteration
- returns: index of next task

Sub SetFinishedDuration(oWhatSheet as Object, iRowNo as integer)
sets the duration for finished tasks

Sub SetInfo(oSheet as object, iRowNo as Integer)
sets the info data

Sub Done()
cleaning up, e.g. closing Progress bar

Sub UpdateGantt
update Gantt graph

Sub Functions
Function CompareTasks(thisCol as integer, Row1 as long, Row2 as long) as integer
- Compares data in Column thisCol of row Row1 and Row2
- returns:
  - -1: if value of Row1<Row2,
  - 1: if value of Row1>Row2,
  - 0: if value of Row1=Row2,
  - 2: if Row1 or Row2 are beyond end

Function GetCellName(oCell as object) as string
returns the name of a cell (e.g. "E6")

## Module "ResourcePlan"
contains the functions for calculating the resource usage
Sub Main
- for each resource in sheet "Resources"
  - for each task with that resource
    - for each time slot in "resources"
      - add effort (relative or absolute)

Sub Init()
- initialize document
- initialize resource sheet and table
- initialize progress bar
- initialize task table

Function GetResourceEffort(oSheet, Col&, RelCol&, Row&) as double
gets the value of (Col, Row) in oSheet or the percentage to RelCol

Sub Done()
- hide progress bar
- close usage of document

# Public Documentation License, Version 1.0
1.0 DEFINITIONS.
1.1. "Commercial Use" means distribution or otherwise making the Documentation available to a third party.
1.2. "Contributor" means a person or entity who creates or contributes to the creation of Modifications.
1.3. "Documentation" means the Original Documentation or Modifications or the combination of the Original Documentation and Modifications, in each case including portions thereof.
1.4. "Electronic Distribution Mechanism" means a mechanism generally accepted for the electronic transfer of data.
1.5. "Initial Writer" means the individual or entity identified as the Initial Writer in the notice required by the Appendix.
1.6. "Larger Work" means a work which combines Documentation or portions thereof with documentation or other writings not governed by the terms of this License.
1.7. "License" means this document.
1.8. "Modifications" means any addition to or deletion from the substance or structure of either the Original Documentation or any previous Modifications, such as a translation, abridgment, condensation, or any other form in which the Original Documentation or previous Modifications may be recast, transformed or adapted.  A work consisting of editorial revisions, annotations, elaborations, and other modifications which, as a whole represent an original work of authorship, is a Modification.  For example, when Documentation is released as a series of documents, a Modification is:
A. Any addition to or deletion from the contents of the Original Documentation or previous Modifications.
B. Any new documentation that contains any part of the Original Documentation or previous Modifications.
1.9. "Original Documentation" means documentation described as Original Documentation in the notice required by the Appendix, and which, at the time of its release under this License is not already Documentation governed by this License.
1.10. "Editable Form" means the preferred form of the Documentation for making Modifications to it. The Documentation can be in an electronic, compressed or archival form, provided the appropriate decompression or de-archiving software is widely available for no charge.
1.11. "You" (or "Your") means an individual or a legal entity exercising rights under, and complying with all of the terms of this License or a future version of this License issued under Section 5.0 ("Versions of the License"). For legal entities, "You" includes any entity which controls, is controlled by, or is under common control with You. For purposes of this definition, "control" means (a) the power, direct or indirect, to cause the direction or management of such entity, whether by contract or otherwise, or (b) ownership of more than fifty percent (50%) of the outstanding shares or beneficial ownership of such entity.
2.0 LICENSE GRANTS.
2.1  Initial Writer Grant.
The Initial Writer hereby grants You a world-wide, royalty-free, non-exclusive license to use, reproduce, prepare Modifications of, compile, publicly perform, publicly display, demonstrate, market, disclose and distribute the Documentation in any form, on any media or via any Electronic Distribution Mechanism or other method now known or later discovered, and to sublicense the foregoing rights to third parties through multiple tiers of sublicensees in accordance with the terms of this License.
The license rights granted in this Section 2.1 ("Initial Writer Grant") are effective on the date Initial Writer first distributes Original Documentation under the terms of this License.
2.2. Contributor Grant.
Each Contributor hereby grants You a world-wide, royalty-free, non-exclusive license to use, reproduce, prepare Modifications of, compile, publicly perform, publicly display, demonstrate, market, disclose and distribute the Documentation in any form, on any media or via any Electronic Distribution Mechanism or other method now known or later discovered, and to sublicense the foregoing rights to third parties through multiple tiers of sublicensees in accordance with the terms of this License.
The license rights granted in this Section 2.2 ("Contributor Grant") are effective on the date Contributor first makes Commercial Use of the Documentation.
3.0 DISTRIBUTION OBLIGATIONS.
3.1. Application of License.
The Modifications which You create or to which You contribute are governed by the terms of this License, including without limitation Section 2.2 ("Contributor Grant").  The Documentation may be distributed only under the terms of this License or a future version of this License released in accordance with Section 5.0 ("Versions of the License"), and You must include a copy of this License with every copy of the Documentation You distribute. You may not offer or impose any terms that alter or restrict the applicable version of this License or the recipients' rights hereunder. However, You may include an additional document offering the additional rights described in Section 3.5 ("Required Notices").
 3.2. Availability of Documentation.
Any Modification which You create or to which You contribute must be made available publicly in Editable Form under the terms of this License via a fixed medium or an accepted Electronic Distribution Mechanism.
3.3. Description of Modifications.
All Documentation to which You contribute must identify the changes You made to create that Documentation and the date of any change. You must include a prominent statement that the Modification is derived, directly or indirectly, from Original Documentation provided by the Initial Writer and include the name of the Initial Writer in the Documentation or via an electronic link that describes the origin or ownership of the Documentation.  The foregoing change documentation may be created by using an electronic program that automatically tracks changes to the Documentation, and such changes must be available publicly for at least five years following release of the changed Documentation.
3.4. Intellectual Property Matters.
Contributor represents that Contributor believes that Contributor's Modifications are Contributor's original creation(s) and/or Contributor has sufficient rights to grant the rights conveyed by this License.
3.5. Required Notices.
You must duplicate the notice in the Appendix in each file of the Documentation. If it is not possible to put such notice in a particular Documentation file due to its structure, then You must include such notice in a location (such as a relevant directory) where a reader would be likely to look for such a notice, for example, via a hyperlink in each file of the Documentation that takes the reader to a page that describes the origin and ownership of the Documentation.  If You created one or more Modification(s) You may add your name as a Contributor to the notice described in the Appendix.
You must also duplicate this License in any Documentation file (or with a hyperlink in each file of the Documentation) where You describe recipients' rights or ownership rights.
You may choose to offer, and to charge a fee for, warranty, support, indemnity or liability obligations to one or more recipients of Documentation. However, You may do so only on Your own behalf, and not on behalf of the Initial Writer or any Contributor. You must make it absolutely clear than any such warranty, support, indemnity or liability obligation is offered by You alone, and You hereby agree to indemnify the Initial Writer and every Contributor for any liability incurred by the Initial Writer or such Contributor as a result of warranty, support, indemnity or liability terms You offer.
 3.6.  Larger Works.
You may create a Larger Work by combining Documentation with other documents not governed by the terms of this License and distribute the Larger Work as a single product. In such a case, You must make sure the requirements of this License are fulfilled for the Documentation.
4.0  APPLICATION OF THIS LICENSE.
This License applies to Documentation to which the Initial Writer has attached this License and the notice in the Appendix.
5.0  VERSIONS OF THE LICENSE.
5.1. New Versions.
Initial Writer may publish revised and/or new versions of the License from time to time. Each version will be given a distinguishing version number.
5.2. Effect of New Versions.
Once Documentation has been published under a particular version of the License, You may always continue to use it under the terms of that version. You may also choose to use such Documentation under the terms of any subsequent version of the License published by______________________ [Insert name of the foundation, company, Initial Writer, or whoever may modify this License]. No one other than ________________________[Insert name of the foundation, company, Initial Writer, or whoever may modify this License] has the right to modify the terms of this License. Filling in the name of the Initial Writer, Original Documentation or Contributor in the notice described in the Appendix shall not be deemed to be Modifications of this License.
6.0 DISCLAIMER OF WARRANTY.
DOCUMENTATION IS PROVIDED UNDER THIS LICENSE ON AN "AS IS'' BASIS, WITHOUT WARRANTY OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, WITHOUT LIMITATION, WARRANTIES THAT THE DOCUMENTATION IS FREE OF DEFECTS, MERCHANTABLE, FIT FOR A PARTICULAR PURPOSE OR NON-INFRINGING. THE ENTIRE RISK AS TO THE QUALITY, ACCURACY, AND PERFORMANCE OF THE DOCUMENTATION IS WITH YOU. SHOULD ANY DOCUMENTATION PROVE DEFECTIVE IN ANY RESPECT, YOU (NOT THE INITIAL WRITER OR ANY OTHER CONTRIBUTOR) ASSUME THE COST OF ANY NECESSARY SERVICING, REPAIR OR CORRECTION. THIS DISCLAIMER OF WARRANTY CONSTITUTES AN ESSENTIAL PART OF THIS LICENSE. NO USE OF ANY DOCUMENTATION IS AUTHORIZED HEREUNDER EXCEPT UNDER THIS DISCLAIMER.
7.0 TERMINATION.
This License and the rights granted hereunder will terminate automatically if You fail to comply with terms herein and fail to cure such breach within 30 days of becoming aware of the breach. All sublicenses to the Documentation which are properly granted shall survive any termination of this License. Provisions which, by their nature, must remain in effect beyond the termination of this License shall survive.
8.0 LIMITATION OF LIABILITY.
UNDER NO CIRCUMSTANCES AND UNDER NO LEGAL THEORY, WHETHER IN TORT (INCLUDING NEGLIGENCE), CONTRACT, OR OTHERWISE, SHALL THE INITIAL WRITER, ANY OTHER CONTRIBUTOR, OR ANY DISTRIBUTOR OF DOCUMENTATION, OR ANY SUPPLIER OF ANY OF SUCH PARTIES, BE LIABLE TO ANY PERSON FOR ANY DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES OF ANY CHARACTER INCLUDING, WITHOUT LIMITATION, DAMAGES FOR LOSS OF GOODWILL, WORK STOPPAGE, COMPUTER FAILURE OR MALFUNCTION, OR ANY AND ALL OTHER DAMAGES OR LOSSES ARISING OUT OF OR RELATING TO THE USE OF THE DOCUMENTATION, EVEN IF SUCH PARTY SHALL HAVE BEEN INFORMED OF THE POSSIBILITY OF SUCH DAMAGES.
9.0 U.S. GOVERNMENT END USERS.
If Documentation is being acquired by or on behalf of the U.S. Government or by a U.S. Government prime contractor or subcontractor (at any tier), then the Government's rights in Documentation will be only as set forth in this Agreement; this is in accordance with 48 CFR 227.7201 through 227.7202-4 (for Department of Defense (DOD) acquisitions) and with 48 CFR 2.101 and 12.212 (for non-DOD acquisitions).
10.0 MISCELLANEOUS.
This License represents the complete agreement concerning the subject matter hereof. If any provision of this License is held to be unenforceable, such provision shall be reformed only to the extent necessary to make it enforceable. This License shall be governed by California law, excluding its conflict-of-law provisions. With respect to disputes or any litigation relating to this License, the losing party is responsible for costs, including without limitation, court costs and reasonable attorneys' fees and expenses. The application of the United Nations Convention on Contracts for the International Sale of Goods is expressly excluded. Any law or regulation which provides that the language of a contract shall be construed against the drafter shall not apply to this License.
Appendix
Public Documentation License Notice
The contents of this Documentation are subject to the Public Documentation License Version 1.0 (the "License"); you may only use this Documentation if you comply with the terms of this License. A copy of the License is available at http://www.openoffice.org/licenses/PDL.rtf.
The Original Documentation is _________________. The Initial Writer of the Original Documentation is ______________________ (C) ____. All Rights Reserved. (Initial Writer contact(s):_______________[Insert hyperlink/alias].)
Contributor(s): ______________________________________.
Portions created by ______ are Copyright (C)_________[Insert year(s)]. All Rights Reserved.   (Contributor contact(s):________________[Insert hyperlink/alias]).
Note: The text of this Appendix may differ slightly from the text of the notices in the files of the Original Documentation. You should use the text of this Appendix rather than the text found in the Original Documentation for Your Modifications.